|  |  |  |  |
| --- | --- | --- | --- |
| **Deliverable** | **Description of the contractual performance provided by the Supplier** | **Completion** | **Payment** |
| D0 | Contract conclusion  | - | - |
| D1 | Export license (if needed) | 3 months from D0 or within extended time limit according to Art. 6.2 hereof if the export license is needed; 1 month from D0 for the Detailed schedule of project activities and work procedures only if the export license is not needed | 40% of the Purchase Price upon acceptance |
| * Conceptual design documentation (including drawing of lab with instrument implementation, end-user statement signed, instrument user manual)
* Detailed schedule of project activities and work procedures
* Bank guarantee
 |
| D2 | Implementation (production) documentation (including part allocation list) + Bank guarantee | 2 months from D1 | 30% of the Purchase Price upon acceptance |
| D3 | Factory acceptance tests of manufactured system at the place of the manufacture (Factory Validation provided by the Supplier) + Brief report | from at least 9 (nine) to at most 12 (twelve) months from the acceptance of D2 | - |
| D4 | Transport and delivery of 3D Atom Probe Tomography to the Client | from at least 9 (nine) to at most 12 (twelve) months from the acceptance of D2 | 20% of the Purchase Price upon acceptance |
| D5 | Installation of 3D Atom Probe Tomography at the Client’s premises (laboratory), Site Validation provided by the SupplierCarrying out a training with the operation of the system lasting at least 3 (three) months | without undue delay after the delivery of the 3D Atom Probe Tomography to the laboratory of the Client | 10% of the Purchase Price upon acceptance |
| Post-warranty service | Post-warranty service (duration one year) | - | 25 % of price for post-warranty service paid in each quarter of providing service |

*Note: The Purchase Price = the total price for the supply as defined by Art. 7.1 of the Purchase Contract*